## Sheet1
Sr.No. | Label | Use_Case_Number | Test case ID | Test_Priority | Name of the Module | Test Designed by | Date of test designed | Test Executed by | Date of the Test Execution | Description/Summary of Test | Scenario Type | Pre-condition | Test Data | Test Steps | Expected Results | Actual Result | Status (Fail/Pass) | Comments
81 | IOC_TEST_PHASE-1 | UC_06 | TC_81 |  | OSS | Durga Kulkarni | 2017-05-03 |  |  | To verify oss is installed on source machine and user successfully login to OSS |  | OSS.exe installed properly. User have account on alibaba User have access key and access secret key of account and security password |  | 1.Log in to source machine | OSS must be installed successfully User should be logged in OSS | OSS installed successfully User Logged in OSS
2.Click on start button
3.Search "OSS" in search bar.
4.Enter Access key and Access secret key
5.Select language and click on Login
6.Set Security Password for Login
82 | IOC_TEST_PHASE-1 | UC_06 | TC_82 |  | OSS | Durga Kulkarni | 2017-05-03 |  |  | To verify that user is able to create bucket for storage. |  | OSS.exe installed properly. User have account on alibaba User have access key and access secret key of account and security password |  | 1.Login to OSS | OSS bucket should be created successfully | OSS bucket created Successfully
2.Click on create button
3.Enter Name of bucket,select region.
4.Set Permission and click on confirm
83 | IOC_TEST_PHASE-1 | UC_06 | TC_83 |  | OSS | Durga Kulkarni | 2017-05-03 |  |  | To verify whether the data (file,image,video)is uploaded in bucket or not |  | OSS.exe installed properly. User have account on alibaba User have access key and access secret key of account and security password |  | 1.Login to OSS | File uploaded successfully | File uploaded successfully.
2.Click on bucket
3.Click on upload and select file
4.See result in uploaded queue.
84 | IOC_TEST_PHASE-1 | UC_06 | TC_84 |  | OSS | Durga Kulkarni | 2017-05-03 |  |  | To verify the created bucket is displayed in Alibaba OSS service |  | Alibaba Account with OSS access |  | 1. Login to Alibaba | Created bucket is present | Created bucket is present
2.Click on OSS
3.Check the created bucket is available or not
85 | IOC_TEST_PHASE-1 | UC_06 | TC_85 |  | OSS | Durga Kulkarni | 2017-05-03 |  |  | To verify uploaded data in particular bucket is present in Alibaba OSS service |  | Alibaba Account with OSS access |  | 1. Login to Alibaba | Files are available. | Files are available.
2.Click on OSS
3.Click on bucket
4.check the data
86 | IOC_TEST_PHASE-1 | UC_06 | TC_86 |  | OSS | Durga Kulkarni | 2017-05-03 |  |  | To verify uploaded file is readable or not. |  | Alibaba Account with OSS access |  | 1. Login to Alibaba | On browsing URL , user is able to read data . | On browsing URL , user is able to read data .
2.Click on OSS
3.Click on bucket
4.check the data
5.Click on Get URL link and click on ok
6.browse the URL and read the file
87 | IOC_TEST_PHASE-1 | UC_06 | TC_87 |  | OSS | Durga Kulkarni | 2017-05-03 |  |  | To verify user is able to delete the data |  | Alibaba Account with OSS access |  | 1. Login to Alibaba | File should be deleted | File is deleted
2.Click on OSS
3.Click on bucket
4.check the data
5.Select the file and click on delete
88 | IOC_TEST_PHASE-1 | UC_06 | TC_88 |  | OSS | Durga Kulkarni | 2017-05-03 |  |  | To verify user is able to delete the bucket |  | Alibaba Account with OSS access |  | 1. Login to Alibaba | Bucket is deleted successfully | Bucket is deleted successfully
2.Click on OSS
3.Click on delete button in front of bucket which user want to delete.